## Stats and Programming
Task | Unit | Cost Per Hour | # of Hours Per Unit | Cost Per Unit | Estimated Cost | Notes
Statistical Analysis Plan and Shells Development (2 Drafts and 1 Final)
Statistical Analysis Plan (SAP) 1st Draft | 1 | 2 | 96 | 192 | 192
Statistical Analysis Plan (SAP) 2nd Draft | 1 | 2 | 32 | 64 | 64
Statistical Analysis Plan (SAP) Final | 1 | 2 | 16 | 32 | 32
Shells (Mock Tables, Figures, and Listings) 1st Draft | 1 | 2 | 70 | 140 | 140
Shells (Mock Tables, Figures, and Listings) 2nd Draft | 1 | 2 | 20 | 40 | 40
Shells (Mock Tables, Figures, and Listings) Final | 1 | 2 | 10 | 20 | 20
Subtotal |  |  |  |  | 488
SDTM Datasets Production and Validation
SDTM Annotated CRFs (aCRF) | 1 | 1 | 32 | 32 | 32 | Assume phase 1 and phase 2 data is collected per 1 CRF
SDTM Dataset Specs (High Complexity) | 5 | 1 | 3 | 3 | 15 | Add the SDTM number from 18 to 25 because some trial (TA/TE/TI/TS/TV) and special purpose domains are needed (SE/SV)
SDTM Dataset Specs (Medium Complexity) | 20 | 1 | 2 | 2 | 40
SDTM Production and Validation: Programs and Datasets (High Complexity) | 5 | 1 | 16 | 16 | 80
SDTM Production and Validation: Programs and Datasets (Medium Complexity) | 20 | 1 | 10 | 10 | 200
SDTM Pinnacle 21 Report Creation and Review | 2 | 1 | 6 | 6 | 12
SDTM Reviewer's Guide | 1 | 1 | 32 | 32 | 32
SDTM Define.xml | 1 | 1 | 32 | 32 | 32
SDTM Dataset File xpt Conversion and Review | 25 | 1 | 0.2 | 0.2 | 5
Subtotal |  |  |  |  | 448
SDTM Dataset Transfer (5 Times)
Production and Validation, the first 2 times | 2 | 1 | 25 | 25 | 50 | 1 hour per domain
Production and Validation, the last 3 times | 3 | 1 | 12.5 | 12.5 | 37.5 | 0.5 hours per domain
Subtotal |  |  |  |  | 87.5
ADaM Datasets Production and Validation
ADaM Dataset Specs (High Complexity) | 5 | 1 | 3 | 3 | 15 | Add the ADaM number from 11 to 15
ADaM Dataset Specs (Medium Complexity) | 10 | 1 | 2 | 2 | 20
ADaM Production and Validation: Programs and Datasets (High Complexity) | 5 | 1 | 18 | 18 | 90
ADaM Production and Validation: Programs and Datasets (Medium Complexity) | 10 | 1 | 10 | 10 | 100
ADaM Pinnacle 21 Report Creation and Review | 1 | 1 | 4 | 4 | 4
ADaM Reviewer's Guide | 1 | 1 | 32 | 32 | 32
ADaM Define.xml | 1 | 1 | 32 | 32 | 32
ADaM Dataset Program xpt Conversion and Review | 15 | 1 | 0.2 | 0.2 | 3
ADaM Program txt Conversion and Review | 15 | 1 | 0.2 | 0.2 | 3
Subtotal |  |  |  |  | 299
ADaM Dataset Transfer (5 Times)
Production and Validation, the first 2 times | 2 | 1 | 15 | 15 | 30 | 1 hour per domain
Production and Validation, the last 3 times | 3 | 1 | 7.5 | 7.5 | 22.5 | 0.5 hours per domain
Subtotal |  |  |  |  | 52.5
Tables, Figures and Listings Development
Unique Table: Production and Validation | 45 | 1 | 10 | 10 | 450
Repeating Table: Production and Validation | 15 | 1 | 4 | 4 | 60
Unique Figure: Production and Validation | 10 | 1 | 10 | 10 | 100
Repeating Figure: Production and Validation | 10 | 1 | 4 | 4 | 40
Unique Listing: Production and Validation | 20 | 1 | 6 | 6 | 120
Repeating Listing: Production and Validation | 20 | 1 | 3 | 3 | 60 | Add 20 repeating listing here
Subtotal |  |  |  |  | 830
Interim Analysis
Interim Analysis #1 SDTM Datasets, Specs, P21 Report | 25 | 1 | 0.75 | 0.75 | 18.75
Interim Analysis #1 ADaM Datasets, Specs, P21 Report | 15 | 1 | 1 | 1 | 15
Interim Analysis #1 Table and Figure Outputs | 80 | 1 | 0.75 | 0.75 | 60
Interim Analysis #1 Listing Outputs | 40 | 1 | 0.3 | 0.3 | 12
Interim Analysis #1 Book-Marked Output PDF File Creation, Review and Delivery | 1 | 1 | 4 | 4 | 4
Interim Analysis #1 LLX Biostats Review | 120 | 1 | 0.1 | 0.1 | 12
Interim Analysis #2 SDTM Datasets, Specs, P21 Report | 25 | 1 | 0.5 | 0.5 | 12.5
Interim Analysis #2 ADaM Datasets, Specs, P21 Report | 15 | 1 | 0.75 | 0.75 | 11.25
Interim Analysis #2 Table and Figure Outputs | 80 | 1 | 0.5 | 0.5 | 40
Interim Analysis #2 Listing Outputs | 40 | 1 | 0.3 | 0.3 | 12
Interim Analysis #2 Book-Marked Output PDF File Creation, Review and Delivery | 1 | 1 | 4 | 4 | 4
Interim Analysis #2 LLX Biostats Review | 120 | 2 | 0.1 | 0.2 | 24
Interim Analysis #3 SDTM Datasets, Specs, P21 Report | 25 | 1 | 0.5 | 0.5 | 12.5
Interim Analysis #3 ADaM Datasets, Specs, P21 Report | 15 | 1 | 0.75 | 0.75 | 11.25
Interim Analysis #3 Table and Figure Outputs | 80 | 1 | 0.5 | 0.5 | 40
Interim Analysis #3 Listing Outputs | 40 | 1 | 0.3 | 0.3 | 12
Interim Analysis #3 Book-Marked Output PDF File Creation, Review and Delivery | 1 | 1 | 4 | 4 | 4
Interim Analysis #3 LLX Biostats Review | 120 | 2 | 0.1 | 0.2 | 24
Subtotal |  |  |  |  | 329.25
Final Analysis
Final Analysis SDTM Datasets, Specs, P21 Report | 25 | 1 | 1 | 1 | 25
Final Analysis ADaM Datasets, Specs, P21 Report | 15 | 1 | 1.25 | 1.25 | 18.75
Final Analysis Table and Figure Outputs | 80 | 1 | 1 | 1 | 80
Final Analysis Listing Outputs | 40 | 1 | 0.5 | 0.5 | 20
Final Analysis Book-Marked Output PDF File Creation, Review and Delivery | 1 | 1 | 4 | 4 | 4
Final Analysis LLX Biostats Review | 120 | 2 | 0.1 | 0.2 | 24
Subtotal |  |  |  |  | 171.75
DSUR First Time
SDTM Specs, Production and Validation Programs | 8 | 1 | 1 | 1 | 8
ADaM Specs, Production and Validation Programs | 3 | 1 | 1.5 | 1.5 | 4.5
TLF Outputs | 5 | 1 | 1 | 1 | 5
Book-Marked PDF File Creation, Review, and Delivery | 1 | 1 | 2 | 2 | 2
Subtotal |  |  |  |  | 19.5
DSUR Rerun (4 times)
SDTM Specs, Production and Validation Programs | 32 | 1 | 0.75 | 0.75 | 24
ADaM Specs, Production and Validation Programs | 12 | 1 | 1 | 1 | 12
TLF (4*5) Outputs | 20 | 1 | 0.75 | 0.75 | 15
Book-Marked PDF File Creation, Review, and Delivery | 4 | 1 | 2 | 2 | 8
Subtotal |  |  |  |  | 59
DSMB/IDMC First Time
SDTM Specs, Production and Validation Programs | 12 | 1 | 1 | 1 | 12
ADaM Specs, Production and Validation Programs | 6 | 1 | 1.5 | 1.5 | 9
TLF (up to 30) Production and Validation Programs | 30 | 1 | 1 | 1 | 30
Book-Marked PDF File Creation, Review, and Delivery | 1 | 1 | 2 | 2 | 2
DSMB Organization, Presentation, Meeting Minutes by DSMB Statistician | 1 | 2 | 16 | 32 | 32
Subtotal |  |  |  |  | 85
DSMB Rerun (2 Times)
SDTM Specs, Production and Validation Programs (2*12) | 24 | 1 | 0.75 | 0.75 | 18
ADaM Specs, Production and Validation Programs (2*6) | 12 | 1 | 1 | 1 | 12
TLF (2*30) Production and Validation Programs | 60 | 1 | 0.75 | 0.75 | 45
Book-Marked PDF File Creation, Review, and Delivery | 2 | 1 | 2 | 2 | 4
DSMB Organization, Presentation, Meeting Minutes by DSMB Statistician | 2 | 2 | 16 | 32 | 64
Subtotal |  |  |  |  | 143
License Fees
Pinnacle 21 Enterprise License Fee for 1 year | 1 | NA | NA | 5500 | 5500
Subtotal |  |  |  |  | 5500
Adhoc Analysis
Exploratory Analysis and Client/Regulatory Request | 200 | 1 | 1 | 1 | 200
Subtotal |  |  |  |  | 200
Project Management/Administration (12 Months)
Project and Timeline Management | 12 | 1.5 | 1 | 1.5 | 18
Meetings/Teleconferences/Emails with Client | 12 | 1.5 | 4 | 6 | 72
Internal Meetings/Teleconferences/Email | 12 | 1.5 | 4 | 6 | 72
Subtotal |  |  |  |  | 162
Grand Total |  |  |  |  | 8874.5